## Roles and Responsibilities
Roles and Responsibilities
Role Title | Team Member Name | Responsibilities
Lead Developer | Gaurav Hasija | *Development of Create account and Log-in functionality and combining it with session to ensure smooth user account functionality. *Ensure that the understanding and technical implementation is clear for every deliverable to the team members. *Evaluate and mitigate technical risks. *Ensure teammates reach out for technical assistance or any clarification related to implementation. *Ensure that the code deliverables are per the assigned task. *Effort estimation for each task and breaking down into workable components. * Coordinate with different module leads to manage timelines, prioritize project tasks and assess risk. * Responsible change management as well as estimating the impacts of these changes in terms of time.
Scrum Master & Database Architect | Lucinda Botlero | * Coordinate with the team to gather requriements and understand current UI standards. * Responsible for proper distribution and handling of UI tasks in the team. * Responsible to report UI progress and any possible risk to the project manager. * Ensure that the project meets specific standards and end-requirements. * Ensure that the project has pleasing and intelligible UI. * Created wireframe for the web application * Created ERD for the developing the database * Created database with sample data. * Created presentation slides.
Co-Programmers | Amar Javaid | * Responsible for the coding of the View Lisitng page (utilized HTML, PHP, CSS). * Managed the connection from the View Lisitng page to the Harvest and Gardner tables in the database using PHPmyAdmin. * Met with Professor to discuss project progress. * Created User Stories related to the View Listing page. * Completed testing on the View Listing page to ensure that the user was able to view details of harvest entries and was able to see contact information of the harvester on every listing.
Co-Programmers | Devin Sparrow | * Responsible for the coding of the Add Listing page(utlized HTML, CSS, PHP) * Managed the connection from the Add Listing page to the Harvest table in the database using PHPmyAdmin * Created User Stories related to the Add Listing page * Completed Testing on the Add Listing page to ensure that it added the user's information to the database and created a new listing on the swap page
Co-Programmers | Lucinda Botlero | * Responsible for the coding of the SwapCenter page(utlized HTML, CSS, PHP,SQL) * Managed the connection from the SwapCenter page to the Harvest table and Gardener table in the database using PHPmyAdmin * Created User Stories related to the SwapCenter page. * Completed Testing on the SwapCenter page to ensure that it returned results as searched by the two different user categories-one a harvester who has something to swap and other, just a general user who is simply browsing.
Co-Programmers | Kayla Covington | * Responsible for the coding of the My Profile page (utilized HTML, CSS, PHP) * Implemented and formatted the Welcome page text with visuals * Implemented and formatted the How It Works page text with visuals * Created User Stories related to the My Profile page * Completed testing on the My Profile page to ensure that the user could properly input and successfully submit their personal information for public viewing on the site.
Project Writer and UI Design | Lucinda Botlero and Kayla Covington | Lucinda:Concept creator and proposal writer for the project. Lucinda:Created Header and Footer for every page except for the welcome and how it works page Kayla: Wrote the official text content for both the Welcome and How It Works pages
Integration and test Lead | Gaurav Hasija | *Integrating all the components of the application to ensure application works as per defined requirements. *Ensuring end to end integration testing *Coming up with test plan for login functionality and test plans for all the feature integrations. *Bug fixes for all modules after first round of testing.

## Team Operating Procedures
Team Operating Procedures
How will the team communicate? | Whatsapp, Zoom, ELMS Messaging, Phone Calls
How often? | Team will collaborate their work on daily basis.
Meeting frequency and times? | Twice a week (frequency may vary based on the deliverable requirements). Time can be adjusted according to everyone's availability.
How will the team collaborate? | Regular communication, Google sheets, Github, Trello
How are decisions made? | Lead explains his/her insight into the matter and the team discussess and reaches a consensus
How are decisions documented? | Trello, Google Sheets, Google Docs

## Effort Estimation and Tracking
Effort Estimation and Tracking
Effort (Person hours)
MAIN ACTIVITY | Sub-tasks | Gaurav Hasija |  | Amar Javaid |  | Lucinda Botlero |  | Kayla Covington |  | Devin Sparrow
|  | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual | Estimated | Actual
Requirements analysis
| Task 1.1 Analyse Requirements | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 2
| Task 1.2 Develop User Stories | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 1
UX / UI /WireFrame
| Task 2.1 UX Design Welcome, HowItWorks / CSS | 1 | 1 | 1 |  | 1 | 1 | 0 | 0.5 | 0 | 0
| Task 2.2 UX Design Login Page / CSS | 1 | 1 | 1 |  | 0.5 | 1 | 0 | 0 | 0 | 0
| Task 2.3 UX Design Signup / CSS | 1 | 1 | 1 |  | 1 | 1 | 0 | 0 | 0 | 0
| Task 2.4 UX Design Swap Center / CSS | 1 | 1 | 1 |  | 1 | 1 | 0.5 | 0 | 0.5 | 0.5
| Task 2.5 UX Design User Profile / CSS | 1 | 1 | 1 |  | 1 | 1 | 0.5 | 0.5 | 0.5 | 0
| Task 2.6 UX Desgn Listing View / CSS | 1 | 1 | 1 | 2 | 1 | 1 | 0.5 | 0 | 0.5 | 0.5
| Task 2.7 UX Design Listing Creation | 1 | 1 | 1 | 0.5 | 1 | 1 | 0 | 0 | 0 | 1
Architecture design
| Task 3.1 Technical Design | 1.5 | 2 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 2
| Task 3.2 Logical Design | 1 | 1.5 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1
| Task 3.3 Database | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 0 | 1
Implementation
| Task 5.1 Welcome related pages of the application. | 2 | 2 | 1 |  | 1 |  | 3 | 2.5 | 1 | 0
| Task 5.2 Login and Sign up feature for users. | 5 | 8 | 2 |  | 3 |  | 3 | 3 | 3 | 0
| Task 5.3 Swap Center Search Listing | 3 | 3 | 4 |  | 4 | 10 | 4 | 4 | 4 | 2
| Task 5.4 User profile features | 2 | 2 | 6 |  | 4 |  | 4 | 3 | 5 | 0
| Task 5.5 Listing features | 3 | 3 | 4 | 10 | 5 |  | 4 | 3 | 5 | 4
| Task 5.6 Integration of all features | 5 | 8 | 2 | 2 | 2 | 3 | 2 | 3 | 2 | 5
Testing
| Task 6.1 Test Plan Creation and Execution | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 1
| Task 6.2 Unit testing | 2 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Task 6.3 Integration testing | 3 | 4 | 0.5 | 2 | 0.5 | 3 | 0.5 | 0.5 | 0.5 | 1
| Task 6.4 Documentation Validation | 1 | 1.5 | 0.5 | 1.5 | 0.5 | 3 | 1 | 2 | 1 | 2
Documentation & Collaboration
| Task 6.1 Group Meeting | 15 | 22.5 | 15 | 22.5 | 15 | 22.5 | 15 | 20 | 15 | 22.5
| Task 6.2 Trello Meeting | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
| Task 6.3 Email Communication | 1 | 1 | 1 | 1 | 1 | 2 | 1 | 1 | 1 | 1
| Task 6.4 Group Chat | 1 | 2.5 | 1 | 2 | 1 | 3 | 1 | 2 | 1 | 2
| Task 6.5 Presentation Documentation | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 1 | 1
TOTAL ESTIMATED and ACTUAL EFFORT per student |  | 57.5 | 77.5 | 52 | 53.5 | 52.5 | 65.5 | 50 | 56 | 49.5 | 52.5

## Project Enviroment
Project Tools/Development Environment
Management/Collaboration/Communication Activity | Selected Tool(s)
Project planning | Google sheet, Trello
Project tracking | Trello
Resource sharing | Github and google drive
Presentation | MS PowerPoint, Google Slides
Team communication | Whatsapp, Phone Call and Email
Engineering Activity | Selected Tool(s)
PHP programming | Visual Studio Code, Sublime
UI programming | Visual Studio Code, Sublime
Database | MySQL (MAMP)
Testing | Google Chrome
Version control | GitHub
UX modeling | LucidChart

## Risk Analysis and Management
Risk Analysis and Management
Top 5 Priority Risks | Prevention or Mitigation actions | Risk description | Probability (Low=1, Medium=2, High=3) | Impact (Low=1, Medium=2, High=3) | Score (Probability x Impact)
Misunderstanding of assigned task | Documentation of the task on trello boards, or clarification meeting when required. | Technical Risk Score (Out of 10)
Lack of knowledge in UI development | Learn the required skill and plan knowledge transfer session from the team. | Lack of knowledge in UI development | 2 | 3 | 6
Lack of knowledge in back-end development | Learn the required skill and plan knowledge transfer session from the team. | Lack of knowledge in back-end development | 2 | 3 | 6
Critical testing Defects | Will recheck and work on the code. | Code repository crash | 1 | 3 | 3
Team member getting sick/illness | Scrum Master assigns task to other member based on the avalaibility. | Critical testing Defects | 2 | 3 | 6
Management Risk Score (Out of 10)
|  | Team member getting sick/illness | 2 | 3 | 6
|  | Team member not being available | 1 | 3 | 3
|  | Inclement weather | 1 | 2 | 2
|  | Team communication | 1 | 3 | 3
People Risk Score (Out of 10)
|  | Misunderstanding of assigned task | 3 | 3 | 9
|  | Not able to work with the time | 2 | 2 | 4